## Tabelle1
Woche 3: Task until 22.1.19
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Build an Android Studio Project | 30 min | 20min | 0 | ALL | Christian
Build a simply typicode/json-server | 2h |  | 2h | Christian
Design a simply MainActivity | 10h |  | 10h | Haris
Login/Register Gui | 10h |  | 10h | David