## Tabelle1
Planning and week goals
15.4 - 21.4
Create Events | Finished
Create and fulfill easter release documents | Finished
Fixing and editing the Login/Register area | Partly
Create the event-page | Finished
22.4 - 28.4 postpone to 29.4 - 5.5 because the team leader was absent.
Building the basic set-up of the eventViewPage
Create the Databasestructure how to store the participants of the reffering event
29.4 - 5.5 new Date 6.5 - 13.5
Differents User can join an event
Admin of an event can invite people
Sprint 9/5
That the user is able to go on the event-view to the referent event.
Comuntication between user via backend.
Sprint 16/5
The event admin should be able to invite people
Editing an event on runtime
User can see his settings that he typed at his registation
User can edit his profile
Sprint 23/5
Working to build up the group area. That should include to create,join,leave and edit an Group. Also events can be create in a group.
Sprint 30/5
See at the notification area when the admin release some important information about an event.
Sprint 6/6
Get some style into the front-end.
Sprint 13/6
Compliting the full program usability and fixing bugs(hopefully not)