## Tabelle1
Woche 3: Task until 22.1.19
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Build an Ionic Project | 30 min | 20min | 0 | ALL | Christian
Build a simply typicode/json-server | 2h | 30min | 0h | Christian | Christian
Design a simply MainActivity | 10h | 13 | 10h | Haris | Haris
Login/Register Gui | 10h |  | 10h | David
Woche 7 until 22.02.19
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Create Tabs in Ionic Project | 10min | 4min | 0h | Christian | Christian
Create a Fab Button where u can choose if u want to create or join an event | 2h | 2.5h | 0h | Christian | Christian
Desgin a simple event card | 1h | 40min | 0h | Christian | Christian
Run a fake api and get data with a get request and show data. | 4h | 3h | 0h | Christian | Christian
Make a simple Adobe Xd design | 5 | 3 | 0 | Haris | Haris