## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Log Login errors when the validation failed | 1h | 1h | 1h | Christian
Fixing the bug when creating an event that it gets update at runtime | 2h | 2h | 0h | Christian
Creating a database design to clear the current mess up. | 2h | 3h | 0h | Christian
Creating all mongodb schemes / User / Event | 4h | 3h | 0h | Haris
Handling http post req when an event is created | 2h | 3h | 0h | Christian