## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Create Invite Component | 4h | 0h | 4h | Christian
Invite other User | 2h | 0h | 2h | Christian
Invited user get a notification | 4h | 0h | 4h | Christian
add a table update to the database | 2h |  |  | Christian
invited user can response whenever he join or refuse | 2h | 0h | 4h | Christian
Finishing settings page funcionality | 5h | 6h | 3h | Haris Jusic
Design the Homepage | 3h | 3h |  | David
Create event collection | 10min | 10min | 0h | Christian
Back-end work that make it possible to invite user to an event | 2h | 2h | 0h