## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Fixing the bug when creating an event that it gets update at runtime | 2h | 1h | 1h | Christian
Creating a database design to clear the current mess up. | 2h | 2h | 0h | Christian
Home Page content | 3h |  |  | David
Create Join Page | 20min | 20min | 0h | Christian
Front end content | 2h | 2h | 0h | Haris Jusic