## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Create Invite Component | 4h |  |  | Christian
Invite other User | 2h |  |  | Christian
Invited user get a notification | 4h |  |  | Christian
add a table update to the database | 2h |  |  | Christian
invited user can response whenever he join or refuse | 2h |  |  | Christian
Finishing settings page funcionality | 5h | 6h | 3h | Haris Jusic
Design the Homepage | 3h | 3h |  | David