## Tabelle1
Planning and week goals
15.4 - 21.4
Create Events
Create and fulfill easter release documents
Fixing and editing the Login/Register area
Create the event-page
22.4 - 28.4
Building the basic set-up of the eventViewPage
Create the Databasestructure how to store the participants of the reffering event
29.4 - 5.5
Differents User can join an event
Admin of an event can invite people