## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Design Login-Page | 3h | 1h | 2h | Haris
Event-View-Ionic-Design | 3h | 3h | 0h | Christian
Log Login errors when the validation failed | 1h | 1.5h | 0h | Christian
Log Registration-errors when the validation failed | 1h | 40min | 0h | Christian
Fixing the bug when creating an event that it gets update at runtime | 2h | 2h | 0h | Christian
Watching the udemy course | 40h | 10h | 30h | Haris/Christian/David
Creating a database design to clear the current mess up. | 2h | 2h | 0h | Christian
Get more knowlegde about smartlinks | 3h | 3h | 0h | Christian
Home Page content | 3h | 0h | 3h | David