## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Save event in event-field after creation | 2h | 1h | 0h | Christian
Create event-view-page | 10min | 10min | 0h | Christian
Make a rebuild of the routing system | 4h | 6h | 0h | Christian
Style Login-Page | 2h | 2h | 0h | Haris
Style Register-Page | 3h | 2h | 0h | Christian
Link to event-view after pressing on an event | 1h | 30min | 0h | Christian
Implement styling of event-view | 1h | 2h | 1h | Christian
Home-Page-Content | 3h | 4h | 0h | David