## Tabelle1
Task | Orginal Est. | Current Est. | Remain | Responsible
Log Login errors when the validation failed | 1h | 0h |  | C. Bachl
Log Registration-errors when the validation failed | 1h | 0h |  | C. Bachl
Fixing the bug when creating an event that it gets update at runtime | 3h | 0h |  | C. Bachl
Setting Page | 1h | 1h | 0h | Haris
Create the Event-View-Page | 4h | 0h |  | C. Bachl
Update the current login design | 2h | 1h | 1h | C. Bachl
Clean up master brunch | 1h | 1h | 0h | C. Bachl