## Tabelle1
Woche 1 until 19.03.2019
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Register/Login-GUI | 3h |  |  | David Cvetkovic
Create Event - Store into Database | 10h |  |  | Christian Bachl
Link between login pages and user | 3h |  |  | Haris Jusic
Woche 2 until 26.03.2019
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Implement Groups | 4h |  |  | Christian Bachl
Data safed on local Data base | 5h |  |  | Haris Jusic
Layout event view | 3h |  |  | Christian Bachl
Login/Register - GUI | 1h |  |  | David Cvetkovic
Woche 3 until 02.04.2019
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Joining/Inviting in/to Events | 10h |  |  | Christian Bachl
Adobe Xd Design implementation | 3h |  |  | David Cvetkovic
Data safed on local data base | 3h |  |  | Haris Jusic
Woche 4 until 11.04.2019
Task | Orginal Est. | Current Est. | Remain | Responsible | Finish
Joining/Inviting in/to Events | 10h |  |  | Christian Bachl
WebApp - Design implementation | 7h |  |  | Haris Jusic, David Cvetkovic